## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1.1 | Installation of Python | MUST HAVE | 1.1 | Durga Sri R | 3- Completed
|  | 1.2 | Providing a dataset containing hotel feedback and customer data. | SHOULD HAVE | 1.2 | Durga Sri R | 3- Completed
2 | 2 | 2.1 | Build a sentiment analysis system to classify feedback into Positive, Neutral, or Negative sentiment. | MUST HAVE | 1.2 | Durga Sri R | 3- Completed
|  | 2.2 | To generate alerts for customer service teams or management when negative sentiment or service issues are identified. | SHOULD HAVE | 2.1 | Durga Sri R | 3- Completed
3 | 3 | 3.1 | Deliver personalized recommendations for amenities, dining options, and activities to guests | SHOULD HAVE | 1.2, 2.2 | Durga Sri R | 3- Completed
|  | 3.2 | Continuously update and refine profiles based on real-time interactions | MUST HAVE | 2.1, 3.1 | Durga Sri R | 3- Completed
4 | 4 | 4.1 | Streamline communication between staff and the system by providing real-time notifications | MUST HAVE | 2.1, 2.2 | Durga Sri R | 3- Completed
|  | 4.2 | Integrate the System with Slack & Email enabling timely responses to guest feedback | SHOULD HAVE | 2.1, 4.1 | Durga Sri R | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 1 | 1 | 5 | 5 | 10 | 5 | 6 | 4 | 3 | 11 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1.1 | Installation of Python | 2024-12-12 | 2024-12-14 | Durga Sri R | Build | 3- Completed | 1 | bar: Day 1
| 1.2 | Providing a dataset containing hotel feedback and customer data. | 2024-12-13 | 2024-12-20 | Durga Sri R | Others | 3- Completed |  | Day 2: 5; Day 3: 5
2 | 2.1 | Build a sentiment analysis system to classify feedback into Positive, Neutral, or Negative sentiment. | 2024-12-23 | 2024-12-28 | Durga Sri R | Design | 3- Completed |  | Day 4: 10
| 2.2 | To generate alerts for customer service teams or management when negative sentiment or service issues are identified. | 2024-12-30 | 2025-01-04 | Durga Sri R | Integration Test | 3- Completed |  | Day 5: 5
3 | 3.1 | Deliver personalized recommendations for amenities, dining options, and activities to guests | 2025-01-06 | 2025-01-12 | Durga Sri R | System Test | 3- Completed |  | Day 6: 6
| 3.2 | Continuously update and refine profiles based on real-time interactions | 2025-01-13 | 2025-01-18 | Durga Sri R | Unit Test | 3- Completed |  | Day 7: 4
4 | 4.1 | Streamline communication between staff and the system by providing real-time notifications | 2025-01-20 | 2025-01-22 | Durga Sri R | Integration Test | 3- Completed |  | Day 8: 3
| 4.2 | Integrate the System with Slack & Email enabling timely responses to guest feedback | 2025-01-23 | 2025-01-25 | Durga Sri R | Integration Test | 3- Completed |  | Day 9: 11
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Wednesday | Setting up virtual environment | Installed VSCode & Python 3.9
2 | Friday | Sentiment analysis & service alert engine | Implemented sentiment analysis and used Groq API Key; generated alerts for negative sentiments
3 | Monday | Personalized Recommendation System & Dynamic Guest Profile Management | Built a system that suggests amenities tailored to individual guest preferences using a hybrid recommendation approach & Continuously update and refine profiles based on real-time interactions
4 | Saturday | Staff Notification & Feedback Integration Hub Deployment | Streamline communication between staff and the system by providing real-time notifications delivered through Slack and Email

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2024-12-12 | 2024-12-20 | Durga Sri R | Start installing the virtual environment |  | Work on gathering datasets of hotels | Setting up VSCode is completed
2 | 2 | 2024-12-23 | 2025-01-04 | Durga Sri R | Start working on the sentiment analysis |  | Implement sentiment analysis | Service alert engine was made
3 | 3 | 2025-01-06 | 2025-01-18 | Durga Sri R | Start to build a system that delivers personalized recommendations |  | Personalized recommendations & profile management | used hybrid recommendation system
4 | 4 | 2025-01-20 | 2025-01-25 | Durga Sri R | Start doing feedback integration |  | Analyzing feedbacks | Generated alerts via Slack & Email channels
5
6
7